## Gantt Chart
GANTT CHART
PROJECT TITLE |  | DataPack Tracker |  |  |  |  | COMPANY NAME | [6 empty] | Tracknet
PROJECT MANAGER |  | Rasik Prajapti |  |  |  |  | DATE | [6 empty] | 2020-07-23 | [14 empty] | Completed | [6 empty] | Remaining | [6 empty] | Due
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (IN WEEK) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [21 empty] | PHASE SIX
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Scope and Goal Setting | Prince & Rasik | 2020-07-23 | 2020-07-30 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Requirement Identification | Jay & Niraj | 2020-07-23 | 2020-07-30 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.3 | Libraries and Classes | Prince & Rasik | 2020-07-30 | 2020-08-13 | 2 | 100% | bar: WEEK 2 M to WEEK 3 F
1.4 | Product Features | Tracknet | 2020-07-30 | 2020-08-06 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
1.5 | Guidelines | Niraj & Utpal | 2020-07-30 | 2020-08-06 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
1.6 | UI for Application | Jay & Prince | 2020-07-30 | 2020-08-27 | 4 | 100% | bar: WEEK 2 M to WEEK 5 F
2 | Software Requirments Specification document
2.1 | System Features | Prince & Rasik | 2020-08-06 | 2020-08-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
2.2 | Functional Requirement | Niraj & Jay | 2020-08-06 | 2020-08-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
2.3 | Non-functional Requirement | Jay & Prince | 2020-08-06 | 2020-08-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
2.4 | Other Requirement | Utpal & Rasik | 2020-08-06 | 2020-08-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
2.5 | Overall Description | Niraj & Utpal | 2020-08-06 | 2020-08-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
3 | Project Implementation
3.1 | Home Screen | Utpal & Rasik | 2020-08-27 | 2020-09-03 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
3.2 | User Authantication | Jay & Niraj | 2020-09-03 | 2020-09-17 | 2 | 100% | bar: WEEK 7 M to WEEK 8 F
3.3 | Database Setup | Prince & Rasik | 2020-09-03 | 2020-09-17 | 2 | 100% | bar: WEEK 7 M to WEEK 8 F
3.4 | Data Usage Calculation | Tracknet | 2020-09-10 | 2020-11-05 | 8 | 75% | bar: WEEK 8 M to WEEK 17 F
3.5 | Bed Time Mode | Prince & Jay | 2020-09-10 | 2020-11-05 | 8 | 75% | bar: WEEK 8 M to WEEK 17 F
3.6 | Emergency Data Bank | Rasik & Niraj | 2020-09-10 | 2020-11-05 | 8 | 75% | bar: WEEK 8 M to WEEK 17 F
3.7 | User Interface for Other Activities | Prince & Rasik | 2020-08-27 | 2020-11-05 | 10 | 80% | bar: WEEK 6 M to WEEK 17 F
3.8 | Tower Finding | Utpal & Jay | 2020-09-10 | 2020-11-05 | 8 | 75% | bar: WEEK 8 M to WEEK 17 F
3.8 | Network speed statistics | Utpal & Niraj | 2020-09-10 | 2020-11-05 | 8 | 75% | bar: WEEK 8 M to WEEK 17 F
4 | Testing
4.1 | Unit Testing | Niraj and Utpal | 2020-11-05 | 2020-11-12 | 1 | 0% | bar: WEEK 16 M to WEEK 16 F
4.2 | Integration Testing | Utpal and Jay | 2020-11-05 | 2020-11-12 | 1 | 0% | bar: WEEK 16 M to WEEK 16 F
4.3 | System Testing | Prince & Rasik | 2020-11-05 | 2020-11-19 | 2 | 0% | bar: WEEK 16 M to WEEK 17 F
4.4 | Acceptance Testing | TrackNet | 2020-11-05 | 2020-11-12 | 1 | 0% | bar: WEEK 16 M to WEEK 16 F
5 | Umbrella Activities
5.1 | Risk Management | Rasik & Prince | 2020-07-23 | 2020-11-05 | 15 | 90%
5.2 | Reusability Management | Niraj and Utpal | 2020-07-23 | 2020-11-05 | 15 | 90%
5.3 | Software Quality Assurance | Jay and Rasik | 2020-07-23 | 2020-11-05 | 15 | 90%
5.4 | Software Project Tracking & Control | Prince & Utpal | 2020-07-23 | 2020-11-05 | 15 | 90%
5.5 | Formal technical reviews | Jay and Niraj | 2020-07-23 | 2020-11-05 | 15 | 90%